## Risk_Register
Risk ID | Asset ID | Asset Name | Threat | Vulnerability | Existing Controls | Likelihood | Impact | Treatment | Risk Owner | Status | Score | Level
R001 | A001 | Customer Database | Unauthorized access | Excessive user privileges | IAM, access reviews | 4 | 5 | Mitigate | Security Manager | Open | 20 | Critical
R002 | A001 | Customer Database | Data breach | Weak database access controls | Authentication, network controls | 3 | 5 | Mitigate | DBA Manager | Open | 15 | High
R003 | A006 | Source Code Repository | Source code theft | Excessive repository permissions | Access control, MFA | 3 | 4 | Mitigate | Engineering Manager | Open | 12 | High
R004 | A007 | Customer Web Portal | Web application attack | Application vulnerabilities | Secure development practices | 4 | 5 | Mitigate | Engineering Manager | Open | 20 | Critical
R005 | A010 | AWS EC2 Servers | Ransomware | Unpatched systems | Endpoint protection, patching | 3 | 5 | Mitigate | Cloud Manager | Open | 15 | High
R006 | A011 | AWS RDS Database | Data loss | Inadequate backup/recovery | Automated backups | 3 | 5 | Mitigate | Cloud Manager | Open | 15 | High
R007 | A013 | AWS IAM | Account compromise | Weak authentication | MFA | 3 | 5 | Mitigate | Security Manager | Open | 15 | High
R008 | A014 | AWS CloudTrail Logs | Log tampering | Insufficient log protection | Centralized logging | 2 | 4 | Mitigate | Security Manager | Open | 8 | Medium
R009 | A021 | Payment Gateway Integration | Third-party compromise | Vendor security weaknesses | Vendor assessment | 3 | 5 | Mitigate | Operations Manager | Open | 15 | High
R010 | A016 | Employee Laptops | Phishing | Insufficient security awareness | Antivirus, email filtering | 4 | 4 | Mitigate | IT Manager | Open | 16 | Critical
R011 | A020 | Email System | Business Email Compromise | Weak phishing awareness | Email filtering | 4 | 4 | Mitigate | IT Manager | Open | 16 | Critical
R012 | A022 | Identity Verification Service | Third-party outage | Vendor dependency | SLA agreement | 3 | 4 | Mitigate | Compliance Manager | Open | 12 | Critical
R013 | A017 | Backup Server | Backup failure | Lack of backup testing | Automated backups | 3 | 5 | Mitigate | IT Manager | Open | 15 | Critical
R014 | A015 | SIEM Platform | Alert overload | Poor tuning | Monitoring rules | 3 | 3 | Mitigate | Security Manager | Open | 9 | Critical
R015 | A018 | Network Equipment | Hardware failure | Aging equipment | Preventive maintenance | 2 | 4 | Mitigate | IT Manager | Open | 8 | Critical
R016 | A019 | MFA System | Authentication failure | Single point of failure | Redundant systems | 2 | 5 | Mitigate | Security Manager | Open | 10 | Critical
R017 | A007 | Customer Web Portal | DDoS attack | Insufficient traffic filtering | Basic firewall | 3 | 5 | Mitigate | Engineering Manager | Open | 15 | Critical
R018 | A008 | Mobile Application | Sensitive data exposure | Insecure storage | Secure coding | 3 | 5 | Mitigate | Engineering Manager | Open | 15 | Critical
R019 | A006 | Source Code Repository | Insider threat | Excessive privileges | Access reviews | 3 | 4 | Mitigate | Engineering Manager | Open | 12 | Critical
R020 | A023 | Security Policies | Non-compliance | Outdated policies | Annual review | 3 | 4 | Mitigate | Compliance Manager | Open | 12 | Critical
R021 | A024 | Audit Reports | Unauthorized disclosure | Improper access controls | Document permissions | 2 | 4 | Mitigate | Compliance Manager | Open | 8 | Critical
R022 | A001 | Customer Database | GDPR violation | Excessive data retention | Data retention policy | 3 | 5 | Mitigate | Compliance Manager | Open | 15 | Critical
R023 | A021 | Payment Gateway Integration | Transaction fraud | Weak monitoring | Fraud detection rules | 3 | 5 | Mitigate | Operations Manager | Open | 15 | Critical
R024 | A010 | AWS EC2 Servers | Cloud misconfiguration | Human error | Change management | 4 | 5 | Mitigate | Cloud Manager | Open | 20 | Critical
R025 | A013 | AWS IAM | Privilege escalation | Misconfigured permissions | Role-based access | 3 | 5 | Mitigate | Security Manager | Open | 15 | Critical
R026 | A016 | Employee Laptops | Device theft | Lack of encryption | Endpoint security | 3 | 4 | Mitigate | IT Manager | Open | 12 | Critical
R027 | A020 | Email System | Malware infection | Unsafe attachments | Email security gateway | 3 | 4 | Mitigate | IT Manager | Open | 12 | Critical
R028 | A005 | Customer Contracts | Data leakage | Improper document handling | Access restrictions | 2 | 4 | Mitigate | Legal Manager | Open | 8 | Critical
R029 | A011 | AWS RDS Database | Service outage | Infrastructure failure | High availability setup | 3 | 5 | Mitigate | Cloud Manager | Open | 15 | Critical
R030 | A017 | Backup Server | Ransomware impact | Backup environment compromise | Backup segregation | 3 | 5 | Mitigate | IT Manager | Open | 15 | Critical

## Risk_Summary
Risk Level | Number of Risks
Critical | 3
High | 6
Medium | 1
Low | 0
Total | 10

## Risk_Heatmap
Impact ↓ / Likelihood → | 1 | 2 | 3 | 4 | 5
5 Critical | 5 | 10 | 15 | 20 | 25
4 High | 4 | 8 | 12 | 16 | 20
3 Moderate | 3 | 6 | 9 | 12 | 15
2 Low | 2 | 4 | 6 | 8 | 10
1 Negligible | 1 | 2 | 3 | 4 | 5

## Risk_Top10
Rank | Risk ID | Risk | Score
1 | R001 | Unauthorized Access to Customer Database | 20
2 | R004 | Web Application Attack | 20
3 | R024 | Cloud Misconfiguration | 20
4 | R010 | Phishing Attack | 16
5 | R017 | DDoS Attack | 15
6 | R022 | GDPR Violation | 15
7 | R023 | Transaction Fraud | 15
8 | R029 | Database Outage | 15
9 | R030 | Backup Compromise | 15
10 | R025 | Privilege Escalation | 15