## Sheet1
Risk ID | Risk Description | Current Score | Risk Level | Treatment Strategy | Planned Control | Control Owner | Target Date | Residual Likelihood | Residual Impact | Residual Score | Status
R001 | Unauthorized access to customer database | 20 | Critical | Mitigate | Quarterly privileged access reviews and PAM solution | Security Manager | 2026-12-31 | 2 | 5 | 10 | Planned
R004 | Web application attack | 20 | Critical | Mitigate | Secure SDLC, SAST, DAST and annual penetration testing | Engineering Manager | 2027-01-01 | 2 | 5 | 10 | Planned
R024 | Cloud misconfiguration | 20 | Critical | Mitigate | Cloud configuration monitoring and security baselines | Cloud Manager | 2027-01-02 | 2 | 5 | 10 | Planned
R010 | Employee phishing attack | 16 | Critical | Mitigate | Security awareness training and phishing simulations | IT Manager | 2027-01-03 | 2 | 4 | 8 | In Progress
R017 | DDoS attack on customer portal | 15 | High | Mitigate | AWS WAF and DDoS protection | Engineering Manager | 2027-01-04 | 2 | 5 | 10 | Planned
R022 | GDPR violation | 15 | High | Mitigate | Data retention reviews and privacy impact assessments | Compliance Manager | 2027-01-05 | 2 | 5 | 10 | Planned
R023 | Transaction fraud | 15 | High | Mitigate | Fraud monitoring and transaction anomaly detection | Operations Manager | 2027-01-06 | 2 | 5 | 10 | Planned
R029 | Database outage | 15 | High | Mitigate | High-availability architecture and failover testing | Cloud Manager | 2027-01-07 | 2 | 5 | 10 | In Progress
R030 | Backup compromise | 15 | High | Mitigate | Immutable backups and backup environment segregation | IT Manager | 2027-01-08 | 2 | 5 | 10 | Planned
R025 | Privilege escalation | 15 | High | Mitigate | Role-based access control and least privilege reviews | Security Manager | 2027-01-09 | 2 | 5 | 10 | Planned
c

## Treatment_Summary
Category | Value | Risk ID | Before | After
Total Risks Identified | 30 | R001 | 20 | 10
Critical Risks | 8 | R004 | 20 | 10
High Risks | 18 | R024 | 20 | 10
Risks Selected For Treatment | 10 | R010 | 16 | 8
Residual Critical Risks | 0 | R017 | 15 | 10
Residual High Risks | 0 | R022 | 15 | 10
Residual Medium Risks | 10 | R023 | 15 | 10
|  | R029 | 15 | 10
|  | R030 | 15 | 10
|  | R025 | 15 | 10